## Action_Points
Action_Points | Description | Rank | Priority | Owner | Assigned Date | Due Date | Status | Notes
2025/09_1 | Hedge at St Michaels requires cutting, Cllr Jarred discussing with KCC |  |  | Louisa | 2025-09-03 |  | 100% | All been re-reported by Cllr Jarred 03/12/2025: Hedges confirmed as clipped
2025/09_2 | Precept Increase to be reevaluated |  |  | Louisa | 2025-09-03 |  | Not Started
2025/09_3 | Status of Pond, obtain quotes |  |  | Gerry | 2025-09-03 |  | 25% | Awaiting agreed collective Scope of Works 3/11: Cllr Jarred to contact KCC for survey of pond with camera
2025/09_4 | Status of Phonebox, obtain quotes |  |  | Gerry | 2025-09-03 |  | Not Started
2025/09_5 | Status of Play Area, obtain quotes |  |  | Gerry | 2025-09-03 |  | Not Started | 22/10/25: Caloo willing to give quote for rubberised surface repair
2025/09_6 | Flowerbeds status of and tidying |  |  | Roger | 2025-09-03 |  | 100% | Tyres being removed and then flowerbeds can be worked 03/12/2025: Tyres removed and soiled banked up
2025/09_7 | Website tidying up |  |  | Louisa | 2025-09-03 |  | 100% | Cllr Jarred been tidying 3/11: Require members of public to advise what needs tidying if PC has missed anything 03/12/2025: Consider closed and will update/migrate appropriate data part of upgrade of website
2025/09_8 | Pond opposite village hall overgrown/unsightly. Clerk to write letter |  |  | Gerry | 2025-09-03 |  | 100% | Letter written but not delivered as deemed PC overstepping jurisdiction
2025/09_9 | Speedwatch require new admin. Cllr Williams offered |  |  | Roger | 2025-09-03 |  | 100% | Cllr Williams has offered to take on role 3/11: Cllr Williams decided too much and so will not be taking on role. PC seeking new admin 03/12/2025: Cllr Vurley, Liz Webb and Charmaine to share responsibilities and see how it goes.
2025/09_10 | Speedwatch - request pricing for 2nd unit |  |  | Gerry | 2025-09-03 |  | 100% | Received reply from Toby, appears problematic to site an additional unit as only 4 poles within village. No quote given as if proceeded ideally need more poles 3/11: On hold as no option for further unit 03/12/2025: AP Closed
2025/09_11 | Parish website - request volunteers for a) speedwatch and b) village cleaning |  |  | Louisa | 2025-09-03 |  | 100% | 3/11: Mentioned again 03/12/2025: Village cleaning volunteers achieved, speedwatch volunteers under 2025/11_02
2025/09_12 | Mill lane overhanging vegetation, Cllr Jarred to pass to Cllr Porter for escalation |  |  | Louisa | 2025-09-03 |  | 100% | 3/11: Cllr Jarred communicated/escalated all overhnging vegetation 03/12/2025: Hedges confirmed as clipped
2025/09_13 | Road repairs, Cllr Jarred to contact Tom Williams (Highways) |  |  | Louisa | 2025-09-03 |  | 25% | Cllr Jarred to have discussion with highways, especially as flooding and need of repairs
2025/10_1 | Access and use of defibrillator. Clerk to discuss with Cllr Jarred on training course |  |  | Gerry | 2025-10-01 |  | 75% | 3/11: Instructions printed and posted by Cllr Jarred. Need to discuss on training | 1 | 874831 | start winter program mid october - complete
2025/10_2 | Salt bins - Clerk to chase up on open cases now that winter is approaching #874831 - replaced with 885606 #863895 #863898 |  |  | Gerry | 2025-10-01 |  | 100% | DDC mentioned priority towards trees in summer hence open cases wouldn’t be attended to untill autumn Church Street Salt Bin resubmitted fault 885606 22/10/25: KCC claim all salt bins have been serviced. Need to recheck and raise any issues as a new case | 2 | 863895 | not coming up
2025/10_3 | Website upgrade/replacement investigate alternative providers |  |  | Clare | 2025-10-01 |  | 100% | 3/11: Cllr Delft reported back on alternative suppliers.
2025/10_4 | Order signage around pond (x3) with updated contact details |  |  | Gerry | 2025-10-01 |  | 50% | Priced at £9.99 per sign, just require updated email and phone details. 3/11: Awaiting email update before ordering | 3 | 863898 | not coming up
2025/10_5 | Price and organise "0300--" telephone number to be used as contact for PC on signage around pond and website |  |  | Gerry | 2025-10-01 |  | 100% | Identified through Telecoms World "0300" number for charity first 3 months 99p and then £9.99 subsequent months Ordered 15/10/2025
2025/10_6 | Clerk to request monthly reports from Councillors. In event of absence expected to be emailed in advance |  |  | Gerry | 2025-10-01 |  | 100% | Clerk had requested in past. To chase again. Email been sent with Cllr Jarred on cc
2025/10_7 | Clerk to add section to agenda for KCC and DDC Reports from Councillors |  |  | Gerry | 2025-10-01 |  | 100% | Added to next PC Meeting Agenda
2025/11_1 | Website - email and domain name update |  |  | Louisa | 2025-11-05 |  | 50% | Cllr Jarred in discussions with Hugo Fox on upgrades | 4 | 885606 | replaces (1)
2025/11_2 | Speedwatch - Need volunteers |  |  | Louisa | 2025-11-05 |  | 25% | 5/11: Mentioned again require additional speedwatch volunteers
2025/11_3 | New bus route Aylesham the #92 |  |  | Gerry | 2025-11-05 | 2025-12-03 | 100% | 5/11: Clerk to post bus timetable on PC website
2025/11_4 | Leylandii trees overhanging on Church street side |  |  | Jane | 2025-11-05 |  | 100% | 5/11: Cllr Vurley to discuss with Charmaine 13/11: Ovendens will trim Leylandi tree, rest of path is OK
2025/12_1 | SID - Appears faulty |  |  | Gerry | 2025-12-03 |  | 25% | 03/12/2025: Appears seal on SID is allowing water ingress. Clerk to contact company for repair/replacement. Email sent to sales@westcotec.co.uk
2025/12_2 | Bus Route Application – there is some new planning in South Aylesham. |  |  | Louisa | 2025-12-03 |  | Not Started | 03/12/2025: Previously bus routes were financed from previous developments. Cllr Jarred to investigate and file