Seend Parish Neighbourhood Plan Steering Group.

MINUTES:  Meeting 31.05.2018  The Pavilion. (Produced by GA V2 19/06/2018)

Attended by : Georgina A’Bear Chair (GA), Kevin Rigg (KR),Peter Newsom  (PN), Darren Nichols (DN) Pamela Akerman (PA)

No members of the public present

1  Apologies: Carola Thorpe & Sarah Chard.

2 Declaration of interest: None

3 Previous minutes 26.04.2018 Approved.

4. Matters arising:

GDPR – GA has circulated the Seend P.C. Data Protection & Privacy Policy to all group members. These are on the P.C. website as well.

At last week’s workshop Georgina Perry from  P.S. gave GA the GDPR handouts as produced by CT  for use at any events we attend.

5. The group discussed the Seend Parish NDP Workshop report of 24th May ‘18 from PS and decided on the following

Local Green Space. At the workshop last week the group reduced the list of Local Green Space sites down to 6 for the next stage of the process. The Horsepond, The top of Love Lane, The green areas in The Lye, BRAG Picnic Area, WI Allotments & P.C. Allotments.

DN is waiting on a template letter from GP(PS) to proceed .This template letter to be used to create the Spotlight article for July. A letter will also be produced to be hand delivered to every house in the Parish. Response to be sent by e.mail or hand del./posted to group members DN/CT &/or CV?

SC also volunteered to GA by phone to e.mail our current list with this information.

The organisation of this to be done via e.mail.

The group also discussed at this point whether there will be a separate survey on the strategic views in the Parish. GA to ask PS this question.

Community Facilities. CV is progressing with this. PS suggested some more sites to be added to the list after their walk around the Parish in the afternoon.

There was a suggestion for the need to purchase Parish On-Line mapping to create maps for the NP. See   finance section.

Visions & Objectives.

As CT & CV had already produced a draft vision statement the group suggested the two of them liase to create a Vision to circulate to the group.

PN is quite interested in the Objectives but it was felt that someone who had been in the group longer may have a better understanding in terms of history and evidence gathered.

The group to read thoroughly the document received today from PS  Vision Toolkit and also wait for the draft template from PS.

6. Community engagement.

DN & PA attended the School May Fayre 19/5/2018. There was limited interest due to the excitement of the other events on the day. A few wristbands were handed out.

GA still to contact Jenny Dalton re Seend Breakfasts.

7. Work is progressing on the Website refresh.

The last minutes to be added.

GA to meet with Amy at Camelot on Thursday 7th June to sit with her and go through website.

8. No correspondence. Received.

9. Spotlight:

The shortlist of 6 sites selected for the Local Green Space process to be advertised and parishioners asked to write in and support sites for progression. DN to wait for the template letter from Georgina Perry at PS  and then write a format for Carola to use in the Spotlight article.

10.Finance;

Grant funding for the new financial year has been approved and we await confirmation of receipt of funds in the Parish Council account.

Carole Vince was repaid £83.00 at the P.C. meeting last week for the purchase of the green silicone N.P. wristbands for promotional material.

GA is to purchase the Parish On Line subscription for £120/year to enable maps to be put into the N.P. All agreed.

Action Plan Review:

GA will discuss this with Place Studio re format & updating.

The group discussed a Workshop in June but felt it was not necessary.

The next workshop with Place Studio Ltd 12th July venue & time tbc

The meeting concluded at 8.50 pm.

Next public committee meeting                                                                                                                         Thursday June 28th 7.30pm  Irene Usher Memorial Hall.

Thursday July 26th  7.30pm Irene Usher Memorial Hall.