## Action_Points
Action_Points | Description | Rank | Priority | Owner | Assigned Date | Due Date | Status | Notes
2025/09_1 | Hedge at St Michaels requires cutting, Cllr Jarred discussing with KCC |  |  | Louisa | 2025-09-03 |  | 100% | All been re-reported by Cllr Jarred 03/12/2025: Hedges confirmed as clipped
2025/09_2 | Precept Increase to be reevaluated |  |  | Louisa | 2025-09-03 |  | 100% | 07/01/2026: Precept kept same as last year. Clerk completed forms and awaiting sign-off from chair before submission
2025/09_3 | Status of Pond, obtain quotes |  |  | Gerry | 2025-09-03 |  | 50% | Awaiting agreed collective Scope of Works 3/11: Cllr Jarred to contact KCC for survey of pond with camera 17/2/2026: Pond day has resulted in a marked improvement in and around pond; still require assessment on water run-off
2025/09_4 | Status of Phonebox, obtain quotes |  |  | Gerry | 2025-09-03 |  | 75% | 19/01/2026: Appears not listed or not on register, have identified paint and have contacted DDC conservation officer for guidance 03/02/2026: DDC advise find contractor and renovate with identified paints to same standard 04/03/2026: Cllr Jarred to find local contractor for painting/refurbishment of Phonebox 05/03/2026: Cllr Williams mentioned neighbour is a decorator who may be able to refurbish the phone box. Clerk mentioned other phone box and was also brought to attention the foundations are listing and needs investigation (AP 2026/03_1)
2025/09_5 | Status of Play Area, obtain quotes |  |  | Gerry | 2025-09-03 |  | 50% | 22/10/25: Caloo willing to give quote for rubberised surface repair 07/01/2026: 2 quotes obtained however are circa £11K, deemed too high. Investigating other approaches 04/03/2026: No Progress
2025/09_6 | Flowerbeds status of and tidying |  |  | Roger | 2025-09-03 |  | 100% | Tyres being removed and then flowerbeds can be worked 03/12/2025: Tyres removed and soiled banked up
2025/09_7 | Website tidying up |  |  | Louisa | 2025-09-03 |  | 100% | Cllr Jarred been tidying 3/11: Require members of public to advise what needs tidying if PC has missed anything 03/12/2025: Consider closed and will update/migrate appropriate data part of upgrade of website
2025/09_8 | Pond opposite village hall overgrown/unsightly. Clerk to write letter |  |  | Gerry | 2025-09-03 |  | 100% | Letter written but not delivered as deemed PC overstepping jurisdiction
2025/09_9 | Speedwatch require new admin. Cllr Williams offered |  |  | Roger | 2025-09-03 |  | 100% | Cllr Williams has offered to take on role 3/11: Cllr Williams decided too much and so will not be taking on role. PC seeking new admin 03/12/2025: Cllr Vurley, Liz Webb and Charmaine to share responsibilities and see how it goes.
2025/09_10 | Speedwatch - request pricing for 2nd unit |  |  | Gerry | 2025-09-03 |  | 100% | Received reply from Toby, appears problematic to site an additional unit as only 4 poles within village. No quote given as if proceeded ideally need more poles 3/11: On hold as no option for further unit 03/12/2025: AP Closed
2025/09_11 | Parish website - request volunteers for a) speedwatch and b) village cleaning |  |  | Louisa | 2025-09-03 |  | 100% | 3/11: Mentioned again 03/12/2025: Village cleaning volunteers achieved, speedwatch volunteers under 2025/11_02
2025/09_12 | Mill lane overhanging vegetation, Cllr Jarred to pass to Cllr Porter for escalation |  |  | Louisa | 2025-09-03 |  | 100% | 3/11: Cllr Jarred communicated/escalated all overhnging vegetation 03/12/2025: Hedges confirmed as clipped
2025/09_13 | Road repairs, Cllr Jarred to contact Tom Williams (Highways) |  |  | Louisa | 2025-09-03 |  | 25% | Cllr Jarred to have discussion with highways, especially as flooding and need of repairs 04/03/2026: Meeting with Highways on 11th Feb 2026 did not take place so No Progress since last meeting. Pothole was fixed outside Cllr Vurley's property and the gentleman (Kieran) explained there is no quality controller in post hence no checks currently. New QC will start 2nd April 2026.
2025/10_1 | Access and use of defibrillator. Clerk to discuss with Cllr Jarred on training course |  |  | Gerry | 2025-10-01 |  | 100% | 3/11: Instructions printed and posted by Cllr Jarred. Need to discuss on training 04/02/2026: Cllr Jarred stated instructions given as use defibrilator so no training required; case closed. | 1 | 874831 | start winter program mid october - complete
2025/10_2 | Salt bins - Clerk to chase up on open cases now that winter is approaching #874831 - replaced with 885606 #863895 #863898 |  |  | Gerry | 2025-10-01 |  | 100% | DDC mentioned priority towards trees in summer hence open cases wouldn’t be attended to untill autumn Church Street Salt Bin resubmitted fault 885606 22/10/25: KCC claim all salt bins have been serviced. Need to recheck and raise any issues as a new case | 2 | 863895 | not coming up
2025/10_3 | Website upgrade/replacement investigate alternative providers |  |  | Clare | 2025-10-01 |  | 100% | 3/11: Cllr Delft reported back on alternative suppliers.
2025/10_4 | Order signage around pond (x3) with updated contact details |  |  | Gerry | 2025-10-01 |  | 50% | Priced at £9.99 per sign, just require updated email and phone details. 3/11: Awaiting email update before ordering 04/03/2026: Awaiting confirmation of new email address with new website before signs can be ordered. | 3 | 863898 | not coming up
2025/10_5 | Price and organise "0300--" telephone number to be used as contact for PC on signage around pond and website |  |  | Gerry | 2025-10-01 |  | 100% | Identified through Telecoms World "0300" number for charity first 3 months 99p and then £9.99 subsequent months Ordered 15/10/2025
2025/10_6 | Clerk to request monthly reports from Councillors. In event of absence expected to be emailed in advance |  |  | Gerry | 2025-10-01 |  | 100% | Clerk had requested in past. To chase again. Email been sent with Cllr Jarred on cc
2025/10_7 | Clerk to add section to agenda for KCC and DDC Reports from Councillors |  |  | Gerry | 2025-10-01 |  | 100% | Added to next PC Meeting Agenda
2025/11_1 | Website - email and domain name update |  |  | Louisa | 2025-11-05 |  | 50% | Cllr Jarred in discussions with Hugo Fox on upgrades 07/01/2026: Cllr Delf and Cllr Jarred held talks with Aubergine and agreed to progress with them for new website 02/02/2026: Signed contract to proceed with Aubergine and paid fee, started delivering information requested 04/03/2026: Website work with Aubergine is ongoing, data is being transferred across. | 4 | 885606 | replaces (1)
2025/11_2 | Speedwatch - Need volunteers |  |  | Louisa | 2025-11-05 |  | 50% | 5/11: Mentioned again require additional speedwatch volunteers 04/02/2026: Nicola and Cllr Williams have volunteered however still looking for further volunteers. 04/03/2026: Cllr Williams has stepped back due to health and work commitments
2025/11_3 | New bus route Aylesham the #92 |  |  | Gerry | 2025-11-05 | 2025-12-03 | 100% | 5/11: Clerk to post bus timetable on PC website
2025/11_4 | Leylandii trees overhanging on Church street side |  |  | Jane | 2025-11-05 |  | 100% | 5/11: Cllr Vurley to discuss with Charmaine 13/11: Ovendens will trim Leylandi tree, rest of path is OK
2025/12_1 | SID - Appears faulty |  |  | Gerry | 2025-12-03 |  | 75% | 03/12/2025: Appears seal on SID is allowing water ingress. Clerk to contact company for repair/replacement. Email sent to sales@westcotec.co.uk 07/01/2026: Awaiting serial number off back to confirm item. 17/01/2026: Confirmed older than 3 years will cost £45 for collection and £55 for assessment on whether can be repaired 17/02/2026: Still awaiting collection from Cllr Williams possession to be assessed for repair 20/02/2026: Rescheduled collection of unit from Cllr Williams now planned for 24/02/2026. 03/03/2026: SID finally collected for assessment from Cllr Williams
2025/12_2 | Bus Route Application – there is some new planning in South Aylesham. |  |  | Louisa | 2025-12-03 |  | Not Started | 03/12/2025: Previously bus routes were financed from previous developments. Cllr Jarred to investigate and file. 04/03/2026: No progress since last meeting. It was mentioned the #92 has only 18 months of funding currently.
2026/01_1 | Road calming - seen in other villages rumble strips with solar powered lighting |  |  | Louisa | 2026-01-07 |  | Not Started | 07/01/2026: Cllr Jarred to imvestigate with Lausanne 04/03/2026: Meeting with Highways on 11th Feb 2026 did not take place so No Progress since last meeting
2026/01_2 | Road and Pavement sweeping schedule - lot of debris around the village |  |  | Louisa | 2026-01-07 |  | Not Started | 07/01/2026: Cllr Porter and Cllr Jarred to enquire in meeting with Highways. 04/03/2026: Meeting with Highways on 11th Feb 2026 did not take place so No Progress since last meeting
2026/01_3 | Litter pick, does nonington have similar option to Aylesham? |  |  | Louisa | 2026-01-07 |  | Not Started | 07/01/2026: Cllr Jarred to ask DDC 04/03/2026: Annual Green Day for volunteers to collect and bag rubbish around village on 14th March followed by refreshments.
2026/01_4 | New bus service #92, is there a chance of a poster on the noticeboards |  |  | Louisa | 2026-01-07 |  | Not Started | 07/01/2026: Clerk mentioned is on website. Cllr Jarred to place printed copy on noticeboards within village
2026/02_1 | Hedge outside Mr Keith Luckhurst impacting visibility up and down street - potential danger |  |  | Louisa | 2026-02-04 |  | Not Started | 04/02/2026: Cllr Jarred to contact Mt Luckhurst and explore if can trimmed at angle to improve visibility.
2026/02_2 | Salt bins - cases although closed issues not resolvd |  |  | Louisa | 2026-02-04 |  | Not Started | 04/02/2026: Cllr Jarred and Cllr Porter to raise at meeting on 11/02 with Highways ideally get Highways to conduct site visit to review status of bins and organise resolution to the reported problem cases
2026/03_1 | Phone box is listing and needs investigation into repair |  |  | Louisa | 2026-03-04 |  | Not Started | It was mentioned phone box due for painting, its foundations are damaged and box is listing so needs investigation into extent and how to repair. Clerk highlighted there is another phone box and this should also be evaluated for refurbishment.
2026/03_2 | Investigate cost of Camera in blocked drain |  |  | Gerry | 2026-03-04 |  | Not Started | investigate cost of putting camera down a drain to assess a blockage. Clerk to gather some online quotes
2026/03_3 | Bins left on the street |  |  | Jane | 2026-03-04 |  | 50% | More bins being left outside and need packing away as becoming a safety issue along the roads. PC to mention to culprits