Grinshill Parish Council

Sub Committee Meeting Agenda

Venue – The Vineyard

28th July 2016- 16.30hrs – 17.30hrs

| Duration | Subject | Lead | Objective |
| --- | --- | --- | --- |
| 2 minutes | Chairman Welcome and Introductions | Paul Jones | Meeting introduction and welcome any new attendees. |
| 2 minutes | Apologies and reasons for absence and approval of meeting minutes. Agree minute taker for today. | Paul Jones | Note any apologies for absence and sign off minutes of previous meeting. |
| 2 minutes | Agenda Share | Paul Jones | Quick run through meeting agenda to provide some focus. |
| 5 minutes | Action Points | Paul Jones | Progress check against designated action point owners. |
| 20 minutes | Mapping Review | All | Share individual mapping thoughts for potential development areas. |
| 20 minutes | Public Meeting | Paul Jones | Initial discussions for planning a public meeting date, content and format. |
| 5 minutes | Village Communications | Paul Jones | Agree any communication that we want to put out to the village and the method. |
| 2 minutes | Agenda Items for next meeting | All | Agenda items and date of next meeting. |
| 2 minutes | Meeting review and close | Paul Jones | Any meeting changes required. |

| Action | Person Responsible | Update (Red, Amber, Green status) |
| --- | --- | --- |
| Send Sub Committee meeting dates to Sue Thomas. | Paul Jones | Action point discharged. |
| Complete CLP funding application and submit to Shropshire Council for approval. | Paul Jones | Action point discharged. Funding has now been approved. |
| Arrange meeting with Shropshire Council to discuss development boundary and CLP options. | Paul Jones | Action point discharged. Meeting held on 28th January 2016. |
| Produce Vision and objectives statement and ask Parish Council to ratify. | All | Action point discharged. Ratified by Parish Council. |
| Place CLP page on village website and update with meeting dates, agendas and minutes. | Paul Jones | Action point discharged. |
| Speak with local estate agents for views about current market interest in commercial requirements. | James Handley | Action point discharged. Detail shared with Sub Committee on 17th March 2016. |
| Arrange meeting with Cllr Adrian Burr to provide progress update of Sub Committee ahead of the next PC meeting | Paul Jones | Action point discharged. Parish Council updated at meeting on 7th March 2016. |
| Produce newsletter article to inform village that CLP is underway and how they can volunteer to help. | Paul Jones | Action point discharged. Newsletter article will appear in April 2016 edition. |
| Produce land ownership map to inform future engagement plan. | Mike Roocroft and Tom Wycherley | Action point discharged. Map shared with Sub Committee on 17th March 2016. |
| Produce 5-6 concepts for potential village future changes for brainstorming session at 21st April 2016 Meeting. | James Handley | Action point discharged. Concept to be kept live for potential future development. |
| Provide maps to James Handley via Brian Bishop or order maps. | Tom Wycherley | Maps now ordered via Shropshire council |
| Attain project and stakeholder plan templates and share with Sub Committee. | Paul Jones | Template attained and plan being populated. |
| Write and submit newsletter article to provide update to Parish Planning. | Paul Jones | Complete. |
| Seek Parish Council endorsement for co-option of new Sub Committee member and go ahead for public meeting planning . | Paul Jones | Complete |
| Sub Committee members to look at high level scoping of potential development. | All | Complete |
| Send meeting minutes to Sue Thomas and ensure village website is updated with Sub Committee documents. | Paul Jones | Complete |