SEEND PARISH PLAN STEERING GROUP                                                                     MINUTES 26/05/2016, 7.30PM  The Pavillion

Attendance Aldetha Raymond,Steve Vaux, Tony Murch, Georgina A’Bear, Pamela Akerman, Sarah Chard.

1. APOLOGIES FOR ABSENCE Carola Thorpe, Kevin Rigg.

2. DECLARATIONS OF INTEREST None

3.APPROVE MINUTES OF PREVIOUS MEETING  CHANGE TREES. AND CV REPLIED. TYPO. CORE STRATEGY. SPOTLIGHT FACEBOOK. Numbers for the website. VB to supply. Changes required

4. MATTERS ARISING (Not already on Agenda)

CT suggested that the minutes need to be more detailed and not to use abbreviations.

SV action plan GA suggested that this becomes an item on the agenda. PA asked if this was agreed that this was a document that we should use as an agenda map.SC suggested that if it was an agenda item as part of the meeting that is updated and reviewed at each stage. This was discussed and agreed to add it as an item.

VB was very keen that we look at the environmental sustainability plan. It was agreed that we need to research this to develop our policies. SV to research this Egan wheel will mean that if we meet these factors then we will match environmental sustainability the NPPF document.

Strategic Environment Assessment. EU SEA  Directive includes basic conditions which SC asked that these be clarified GA to ask VB. SV to start researching the process and its requirements.

5. Sub-Groups.

Traffic Sub group report on Highway Workshop 9/06/2016

The workshop has been arranged and the group are working hard to develop plans.

Footpaths and byways. KR to provide information of who the group are.

6. Wiltshire Council on N.P. Area Designation. The process has started and ends on 30th June 2016.

7. Neighbourhood Plan. The next step/ questionnaire preparation SV suggested that we publish the headers and have another public consultation.

SV researched costs for sending out a questionnaire and these were expensive for the return and speed of actions.

SC has suggested that we draft a conclusion and then go back to a public consultation.

CT and GA have produced a letter and have started to have replies GA and CT to observe this process and replies.

SV has produced a Communications Strategy. This was discussed CT had some amendments to this document.    .

Business Engagement. SV has started a spreadsheet with local business details on. Further discussions required.

Headlines in local papers may be causing concerns. CT suggested that we walk that village, but it was suggested that Google earth may give us a good view of different sites.

CT's email read by GA and the group discussed and agreed that the group are working towards a positive outcome.

Community involvement with land owners. It was suggested that it would be difficult to contact this group. Discussions on methods to engage this group. Under 18`s another group was highlighted as needing contact. Again would prove difficult to monitor and contact.

8. Seend Parish Housing Needs Survey. Awaiting information. Expected to have  a basic knowledge that can be reported in the June meeting.

9. WEBSITE / FACEBOOK & EMAILS. Website visitors 102 visitors look at 280 page views. Use this email for group as correspondence.

10. Spotlight Article CT will produce this article and GA will provide information that the group wish to be highlighted, such as business engagement, Highways report from  workshop and N.P. Area Designation report. July and August Spotlight.

11. FINANCE

Grant Applications. SC has sent an email which explains the principles of the grant. Take information from Sarah's email....

Dr Nigel Knott funded flyer in the recent spotlight. Thanks given by the group and Chairperson.

12. A.O.B. Members are reminded to contact the Chair if unable to attend meetings  and review draft minutes and the action plan document for any action plans allocated.

Is the Electoral roll available to groups like ourselves. GA to find out from VB.

Action plan review and group update amended. This will be attached to the draft minutes.

Meeting closed 10pm.

Dates of next meeting.

Thursday 23rd June Knightsmead Farm, Inmarsh, SN12 6RX

Thursday 28th  July The Pavillion.

Minutes Produced by Aldetha Raymond