Broadband Fibre to the Premises (FTTP) 									Update 12            May 16th  2023

In Summary

- At the March PC meeting, we expected building of the network to start in mid/late March.

- Sadly, we have been defeated by the weather and construction has still not started.

The Construction Phase

- The Met office reported “England’s wettest March since 1981 and the third wettest on record.”

- Followed by above average rainfall in April and now in early May.

- Below average temperatures and lack of sunshine have not helped.

- Consequently, landowners have refused access to Wessex and this situation remains.

- I have spoken with Wessex every week pressing them for a start date, but they are in landowners’ hands.

- The first fibre to be laid will run from the Ansty Farm shop area and into DSA alongside Sans Lane

- The build will be managed by Project Manager Tony Najdoski.

- The build foreman is Mark Ricketts.

Agreeing the route of the fibre network (Designed by Rebecca Wells, Wessex Network Planner)

- Wessex continue to try to resolve some routing challenges. This will not delay the start of the build.

- The main routing challenges are on Lower Street North and St Bartholomew’s Street.

- The good news is that SSE have now given permission to use their infrastructure.

- We did not want to use their poles and ducts but if we cannot gain access under private gardens, we will resort to using the SSE infrastructure.

- Josh (Engagement Mgr) and Mark Ricketts (Foreman) Wessex have offered to ‘walk the route’ of the fibre network with me, in late May.

Connecting St Andrew’s church to the network

- Last year, Wessex agreed to provide full fibre to the church for a nominal £1 per month.

- On May 31st, Josh from Wessex will meet Anna Harding from Salisbury Diocese to discuss the installation.

- It is hoped that Ms Harding will ensure the necessary diocesan permissions are granted quickly to Wessex.

Other areas of DSA which will not benefit from the work above – ‘the 89 properties’.

By way of a reminder.....

Properties (UPRNs) in the parish 		= 238

Minus 9 tennis courts and 7 duplicates	= 222

Minus 95 covered by Wessex scheme 	= 127

Minus 38 who already have Fibre to The Property (FTTP to the old Ferne and Wardour schemes) = 89

- The 89 were subject to the Governments ‘Public Review’ of the whole of Wiltshire, carried out by BDUK in 2022.

- I have spoken to and exchanged emails with Graham Huxter, WCC Broadband Manager. He was only able to confirm what we already know about the Public Review

- Therefore, I have discussed further with Wessex.

- They have agreed to consider extending the Village Centre Scheme (the 95 properties) to cover the remaining 89

- Provided we obtain registration of 50% of the 89 properties – we have called this the Southern Scheme

- Once the Village centre Scheme is underway, we will start campaigning.

- I have some marketing materials and a map of the village showing the extent of the existing fibre network.

Communications

- The last Wessex update was sent on February 6th to all householders who have ordered the Wessex service.

- I have pressed Wessex for more regular updates - in particular, in relation to the current weather delay.

- Josh has committed to a regular update on or around the 18th of each month.

Nick Martin, Simon Barkham -  May 16th 2023