Christmas Lights Event - 1st December 2019

Progress Report

| Activity | So far… | Actions to be progressed |
| --- | --- | --- |
| Santa’s Grotto | In the Assembly Rooms 12noon - 4.45pm – to maximise the time available as very popular. Eddie Gee to continue as our Santa Supporting Entertainment - Crazy Elf - booked to entertain the queues Dottie’s Little Sparkles – booked for foyer – glitter face painting | Santa’s Grotto to be organised Presents to be counted, purchased & wrapped Room to be laid out day Min 4 volunteers needed in Assembly Rooms to manage queues, take money etc |
| Stalls | 22 market stalls booked so far - 5 Electricity requests booked – £5 each 4 Gazebos hires booked - £15 each | Keep pushing for more traders |
| Entertainment programme | KLFM – Adam Newstead – breakfast show - hosting with Town Crier. Thursford Organ – booked King’s Morris Dancers – booked for outside Red Lion PH PA system – booked - speakers and pa system, incl. headsets for singers on stage Timescape – booked Fakenham Town Band – booked RockavoX - booked- independent choir from Dereham/Swaffham Ian Clews – booked |  |
| Town Crier | Helping host the day and the Raffle alongside KLFM |  |
| Road Closure | Booked - on the West side from the Buttercross mini roundabout to Swaffham Café | Notices posted Road Closure signs with posters to advise why there is a road closure |
| LIVE Animal Nativity | Booked for set up in Plowright’s Place Hand Wash facilities arrangements in place | Water to be sourced |
| Funfair | Booked - adult Funfair outside Assembly Rooms/Swaffham Café Booked – children’s small funfair – Market Place |  |
| Raffle | 14 Raffle prizes so far pledged from local businesses. 1st prize – £200 2nd prize – KLFM studio tour & sit in on a show Plus 25+ vouchers & prizes 1000 tickets printed Cllrs selling on Sat market Local businesses also selling Remainder to be sold on the day. |  |
| KLFM | Adam Newstead, breakfast show host booked for full event. Will play KLFM jingles & music as filler between acts, help with announcements, light switch on and raffle. KLFM will also publicise the event |  |
| Event Brochure | 17 adverts agreed - £850 income 300+ brochures printed Copies circulated to local businesses, Saturday Market traders & customers, social media & council website. | 200 copies to be printed and circulated prior to the event 100/200 copies to be printed for the day itself. |
| Council Gazebo | Information point / Selling Raffle tickets on the day / Handing out event programmes / Managing the event | Volunteers needed to manage the event on the day Road closure, trader arrival sell raffle tickets hand out event brochures manage entertainment programme – acts & KLFM, Town Crier etc mange traders monitor toilets & bins monitor Live Animal Nativity information & lost children point lights switch on clean up – market, Assembly rooms, road closure & reopening |

Promotion

Going well -

| Posters | A4/A3 – lampposts - DONE |
| --- | --- |
| Banners | Brandon Road, Necton Petrol Station, Downham Market Roundabout, A47 roundabout |
| Social Media | Facebook, twitter, #Swaffham Hour - DONE |
| KLFM | Radio adverts & mentions - DONE |
| Breckland | Events website - DONE |
| Newspapers | Lynn News/EDP/Watton & Swaffham - DONE |
| Swaffham Newsletter | Poster and regular mention - DONE |
| Saturday Fun Run | poster/banner weekly in Nov |
| Hand out for | A4 hand out for shops – volunteers to talk to local shops - DONE |
| Event Brochure | November circulation – businesses, social media, weekly Sat gazebo etc - DONE |
| Council Gazebo | Nov – weekly selling raffle tickets & handing out programmes - DONE |
| Market Traders | Handing out Event programmes - DONE |
| Local Community | Posters/Event programmes in Library, Assembly Rooms, Community Centre, Superstores |

# Text boxes

Buttercross

Uncle Lukes, Swaffham

Preparing a bespoke PVC covering that will provide a weatherproof barrier to

- allow performers on the Buttercross to shelter from wind, rain etc

- allow sound to be projected onto the market place

- provide a backdrop to advertise the event & potential sponsors

The cover will be

- bespoke in nature to Swaffham Town Council – using our logo and name

- generic enough that we can reuse it time and again for different events – ave. 4/5 events per year.

This is a separate events budget purchase approved by the Council in October 2019.