| TIMELINE - Swaffham Neighbourhood Plan | 14 | 15 | 16 Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 17 Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 18 Jan | Feb | Mar |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Research & Training | ( | ( | ( | ( |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Agree to prepare NP & Designated Area |  | ( | ( | ( |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Agree Statement & Vision |  |  | ( | ( |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Notify Breckland Council |  |  |  | ( |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Designation of Neighbourhood Area |  |  |  |  | ( | ( |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Apply for DCLG Grant |  |  |  |  |  | ( | ( | ( | ( | ( | ( | ( |  |  |  | * | * |  |  |  |  |  |  |  |  |  |  |  |  |
| Apply for Breck. Council Grant |  |  |  |  |  | ( | ( |  | ( | ( |  | ( | ( |  |  | * | * |  |  |  |  |  |  |  |  |  |  |  |  |
| Apply for Tesco S.106 money |  |  |  |  |  | ( | ( | ( | ( |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify and engage key partners |  |  |  | ( | ( |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify Issues and Aims |  |  |  | ( | ( | ( |  | ( | ( |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Initial Community Engagement |  |  |  |  |  | ( | ( |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Appoint key Planning Adviser |  |  |  |  |  |  | ( | ( | ( | ( |  | ( |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review existing and draft Local Planning Policies |  |  |  |  |  |  | ( | ( | ( | ( | ( | ( | * | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review Issues and Aims |  |  |  |  |  |  |  |  | ( | ( |  | ( | * | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop policies, proposals, site allocations |  |  |  |  |  |  |  |  |  | ( | ( | ( | * | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Consult with all key partners |  |  |  |  |  |  |  |  |  | ( | ( | ( | * | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review policies, proposals, site allocations |  |  |  |  |  |  |  |  |  |  |  | ( | * | * |  |  |  | * | * |  |  |  |  |  |  |  |  |  |  |
| Ongoing Community Engagement |  |  |  |  |  |  |  |  |  |  |  | ( | * | * |  |  |  | * | * |  |  |  |  |  |  |  |  |  |  |
| Building, reviewing, adapting Evidence Base |  |  |  |  |  |  |  |  |  |  |  |  |  | * | * | * | * |  |  | * | * |  |  |  |  |  |  |  |  |
| Proposed Neighbourhood Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | * | * |  |  |  |  |  |  |
| Statutory Consultation (6 weeks) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | * | * |  |  |  |  |  |
| Submit to Breckland Council (publicity 6 weeks) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | * | * |  |  |  |  |
| Independent Examination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | * | * |  |  |  |
| Modifications |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | * | * |  |  |
| Referendum (28 working days) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | * | * |  |
| Bring Plan into Force |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | * | * |