MILBORNE ST ANDREW

NEIGHBOURHOOD PLAN WORKING PARTY

MEETING HELD ON 13th JANUARY 2015 AT THE VILLAGE HALL COMM. ROOM

No.5

- Present: Mike Brown (MB), Georgina Carrington (GC), Sue Cherry (SC), Michael Hopper (MH), Ronald Hogg (RH), David Gould (DG), Susan Gould (SG).        Not present: Brian Burton (BB)

- The Minutes of Meeting No.4 on 10th December 2014 were approved with no amendments.  Matters arising;

  - (2a) Public Liability Cover: Clerk of the council has confirmed that we are covered when on NP business

  - (5b) The Clerk has also agreed to hold the NP grant, and will act as treasurer.  MH to keep a record of expenditures.	MH

- There were no declarations of interest, based on the contents of the Agenda.

- Updates on tasks:

  - Work on a facebook site to be deferred until next meeting	GC

  - Two people have been approached regarding a web page.  No decision yet.  Research showed that fees would be payable to buy a domain name, and that rent for space on the internet varied according to the amount of pages required.  There are several template formats available to construct a simple website.  MH and SG to continue research.	MH/SG

  - The Village Hall Committee Room has been booked provisionally for the 2nd Tuesday in each month until December.  As the funds have now been deposited in the PC Bank Account, this will now be confirmed.  Two full days to be booked for open days (1 weekday, 1 weekend) (dates below)	SC

  - The cost of a banner is around £55 for 8ft x 3ft.  To be designed with words similar to “Open day today in VH Comm. Room” etc.  Maybe also an A frame format based on approved flyer.  All invoices to be paid before 31st March 15.	DG

  - Vision statement discussion deferred until next month	MH

  - SWOT analysis to be deferred until next month (may be used as part of open day)	MH

  - Housing Needs Survey – GC produced the 2007 for the Abbey Ward, useful info included details of percentage private/social rental, and a breakdown of household types.  GC to email Nick Cardnell to ask for a Freedom of Information anonymized recent housing needs survey specifically for MSA	GC

  - Estimate of administration costs.  After discussion, it was decided to estimate and purchase enough materials for the open days, which includes paper, ink cartridges, pens etc.  SG to purchase	SG

- Involvement of Residents

  - Finalisation of dates:  Due to the chaos of flood alleviation work outside the VH, and the very inclement weather this time of year, it was decided to postpone the Open Days until March and April.  Weekend dates: 1st choice in March is Sat 21st, 2nd choice 28th. Rental time 9.30 to 3.30, Open time 10 – 3.  Weekday dates will be after the Easter holiday (a big gap in case the format needs changing). 1st choice Fri April 17th (Library van day) 2nd choice 24th April.  Duration the same as above.  Update: Sat 21st March and Friday 17th April booked.

  - Format of open days

    - GC has obtained some A1 maps of MSA, SG to investigate cost of laminating, acetate markers to be used to highlight any info.  More decisions next month.	SG

    - Nick Cardnell has agreed to source display boards for the open days. DG to confirm date with him.

  - Flyer was approved, after getting 4 quotations, it was decided to go with Weyprint, who also print the MSA Reporter.  Chosen as quality could be guaranteed, and they will deliver to village.

  - Next Reporter Article to be roughed out by GC, SG to refine and send on.

- Any Other Business:

June Maitland kindly obtained a copy of the Shillingstone NP Questionnaire, Update:  Info from JM, John Paul, chair of the Shillingstone NPG has offered assistance.

- Next Meeting: Is set for Tuesday 7th February 15 in the VH Committee Room at 7pm.