# ACTION PLAN 2025/26

# Introduction

# The purpose of this document is to set out the activities and projects Lenham Parish Council will commence or complete within 2025/2026. Parish Councils are an essential part of the structure of local democracy and have a vital role in acting on behalf of the communities they represent. They:

# give views, on behalf of the parish, on planning applications and other proposals that affect the parish,

# undertake projects and schemes that benefit residents,

# work with partners to achieve benefits for the parish,

# alert relevant authorities to problems that arise or work that needs to be undertaken,

# Engage and support the community, including parishioners, local businesses, community groups and organisations in Lenham,

# help the other tiers of local government stay connected with their local communities.

# Parish Councils have a wide range of powers which relate to local matters, such as maintaining, the recreation ground (William Pitt Field), play parks (Ham Lane and Cherry Close) and other open spaces (including Cherry Downs picnic site, St Mary’s Churchyard  and Lenham’s memorial chalk cross).

# They also have the power to raise money through the precept, which is the parish council’s share of the council tax.

# Implementation

# All staff and Councillors have a responsibility to ensure the action plan is implemented within existing resources.

# Monitoring

# The Action Plan will be monitored by the Clerk with regular updates on progress towards the actions reported back to the Parish Council along with associated budget reporting.

# Action Plan

| NUMBER | ACTIONS | COMMENTS | TIMESCALE |
| --- | --- | --- | --- |
| GENERAL |  |  |  |
| 1 | Comment on all planning applications which fall within or impact on the Parish. | Overseen by Planning and Implementation Committee. | Ongoing |
| 2 | Maintain an up-to-date website and social media presence in the village in line with the Communications Policy. | Staff and allocated members | Ongoing |
| 3 | Identify and secure sources of funding to advance LPC priorities. | Full Council and officers | Ongoing |
| 4 | Maintain good governance, including adhering to relevant benchmarks to work towards achieving Quality/Gold Status of the Local Council Award Scheme. | Full Council and officers | Ongoing |
| 5 | Monitor financial budgets throughout the year and maintain strict expenditure control in line with Financial Regulations | Finance and General Purposes Committee and officers | Ongoing |
| 6 | Listen, investigate and respond to issues identified by the parish of Lenham and, if appropriate, to signpost to the correct person/ organisation for resolution/ further progression. | Full Council and officers | Ongoing |
| 7 | Open office to the public to allow the public access to the parish council. | Officers | Ongoing |
| 8 | Work with and support local groups for the improvement of the facilities, environment and social and economic wellbeing in the community. | Full Council and officers | Ongoing |
| 9 | Deliver speedy and transparent decisions through full meetings of the Council, supported by appropriate committees and working groups. | Full Council | Ongoing |
| 10 | Promote training and induction and ongoing support for members of staff and councillors. | Full Council and officers | Ongoing |
| 11 | Deciding priorities for the use of CIL funds allocated directly to Lenham Parish Council. | Full Council and officers | Ongoing |
| 12 | Work with Kent police and other partners to help combat crime and anti-social behaviour. | Full Council and officers | Ongoing |
| 13 | Organise and arrange in conjunction with St Mary’s Church the annual Lenham Remembrance Service. | Chair and clerk | October/ November |
| SPECIFIC ACTIONS FOR 2025/26 |  |  |  |
| 14 | Progress actions identified in the Highways Improvement Plan (including improvements to the A20 in liaison with KCC Highways and Kent Police)). | Overseen by Planning and Implementation Committee. | Ongoing |
| 15 | Recruitment of temporary post to cover maternity leave. | Staffing Committee | Jun-25 |
| 16 | The clerk to work towards achieving CiLCA qualification. | Clerk | Jun-26 |
| 17 | Review the Lenham Neighbourhood Plan. | Neighbourhood Plan working Group | 2031 |
| 18 | Arrange a village spring clean and litter pick. | Cllr. D Turner | May-25 |
| 19 | Organise volunteers and order plants for the village planters. | Cllr. D Garland | May 2025 and October 2025 |
| 20 | Set up Speedwatch in Lenham Village. | Cllr. J Britt | Ongoing |
| 21 | Progress Tourism Group Actions (see specific action plan). | Cllrs. S Heeley, K Hammond and M Michaelas. | Ongoing |
| 22 | Consider enhancements to the Cherry Downs picnic site. | Cllr. N Osborne | Ongoing |
| 23 | Progress plans for the new recreation ground. | Full Council - allocate to a working group | Ongoing |
| 24 | Organise and host an event for VE 80 celebrations. | Allocated members and Deputy Clerk | May-25 |
| 25 | Organise an Easter Trail event. | Deputy Clerk | Apr-25 |
| 26 | Represent residents about the proposed Heathlands Garden Community Development at Lenham Heath. | Cllrs. J Britt and K Hammond | Ongoing |
| 27 | Maintain Lenham’s War Memorial Cross and organise regular working parties. | Cllr. A Ratcliffe and officers | Ongoing |
| 28 | Maintain Lenham Cemetery and associated records. | Officers | Ongoing |
| 29 | Review the parish emergency plan. | Cllr. J Britt | June 2025 |
| 30 | Upgrading the children’s play areas at Ham Lane and Cherry Close. | Deputy Clerk | Aug-25 |
| 31 | Progress project to extend Maidstone Road car park. | Cllrs. J Britt, D Garland, N Osborne, A Ratcliffe & A Walmsley | Ongoing |
| 32 | Complete refurbishment of public toilets. | Cllrs. D Garland and A Ratcliffe | May-25 |
| 33 | Complete replacement floor and refurbishment of office. | Cllrs. D Garland and A Ratcliffe | Apr-25 |
| 34 | Installation of three defibrillators in rural locations. | Cllr. D Earl | May-25 |
| 35 | Upgrade the CCTV in the village and develop a CCTV use and management guide. | Cllrs. J Murray, D Garland, N Osborne and A Walmsley | Mar-26 |
| 36 | Explore potential to set up a village Wifi system. | Cllrs. J Murray and D Garland | Mar-26 |
| 37 | Complete repairs to the cemetery road. | Cllr. A Ratcliffe and officers | Mar-26 |
| 38 | Progress project for the building of a new nursery at the allotments site. | Cllrs. N Osborne and A Ratcliffe | Ongoing |
| 39 | Complete tree surveys at all sites and complete recommended works | Cllr. D Garland | Jun-26 |
| 40 | Maintain and complete regular operational inspections of play parks |  | Ongoing |
| 41 | Organise the annual parish meeting | Cllrs. and Officers | Once a year (April to June) |