## Sheet1
| Infrastructure 2021/22 | 1140
| Infrastructre 2022/23 | 2000
| Total funds available | 3140
ITEM | BUDGET | COST exluding VAT | COUNCIL MEETING | NOTES
Osborne House clock | Infrastructure | 1244 | September 2022 FC | Work completed - invoice to be paid in Feburary 23
Rushlake Green Village Sign | Infrastructure | 855 | September 2022 FC | Work has yet to commence
Rushlake Green Noticeboard Refurbishment | CIL | 325 | January 2023 FC | Contractor has been informed
Two new benches for Rushlake Green | CIL | 1617 | July 2022 FC | Estimated delivery to Cllr Long's address 27/2/2023
Two new picnic benches for Rushlake Green (£384 each) | CIL | 768 | September 2022 FC | Delivery would be extra charge which has been agreed
Up to 4 picnic benches for BSG Village Hall | CIL | 1600 | July 2022 FC | Design to be agreed at Jan 23 Environment meeting - maximum of an additional £100 for delivery
TOTAL AVAILABLE FUNDS as at 22.1.2023 |  | 1041
NEW INFRASTRUCTURE BUDGET 23/24 available from the 1.4.23 |  | 427
TOTAL INFRASTRUCTURE BUDGET AVAILABLE |  | 1468
Additional projects
Kissing gate to be replaced with a five bar gate |  | EST cost 1500 | Item 7.2. AGREED at the Oct 22 Environment meeting | The Clerk has not yet actionned
New flag - Highlighted as an item that needed to be replaced |  | EST cost 100 | Item 7 at the Oct 22 Environment meeting | Cllr Saunders to store and test the new flag pole.
Replacement fencing at Peter Croft memorial - Highlighted as an item for future repair work |  | EST cost 1000 | Item 7 at the Oct 22 Environment meeting | Clerk to get quotes - not yet actionned
Bike rack |  |  | July 22 Environment meeting | Clerk to invesitgate options after her 6 priorities had been completed