Minutes of NP Steering Group Public Meeting

Monday 13th July at 8pm

|  | Item | Notes | Actions |
| --- | --- | --- | --- |
| 1 | Apologies | Richard Hellier, Philippa May Present: Wendy Makepeace-Brown, Richard Eastment, Tina Collins, Judy Johnson |  |
| 2 | Minutes of previous meeting | These were approved | JJ to forward July Mins to Clerk. WMB to print off all Minutes of SG for RE to sign and pass to JJ to file |
| 3 | Declarations of interest | None |  |
| 4 | Treasurer’s Report (WMB) | WMB summarised our situation and resources for the benefit of members of the public |  |
| 5 | Update in training course for Get Mapping (WMB | WMB has made all relevant bookings. David Jackson has offered to do our NP mapping and RE will assist him once we have assessed sites | RE to liaise with DJ. JJ and WMB to attend trainings on 20.7.15 |
| 6 | Update on Plan progress | RE explained delays in progress due to Watery Lane Appeal and that we currently await Hart District Council decision on Grove Farm due 29.7.15. As the outcome at WL has a significant impact on our plan we agreed to send out a new tender to three agencies including Plan-et to price for the remaining work with a deadline of Dec ’15. We discussed increasing our membership on the SG but agreed to defer this as an agenda item for the next meeting | WMB to send JJ contacts for 2 consultancies. JJ to draft and agree a tender and circulate asap with a 30 day deadline. |
| 7 | Dates for forthcoming meetings with Plan-et Consultants, NP groups and HDC (WMB) | We agreed 2nd Monday of each month from Sept as WMB may not be able to attend all Monday meetings with alternates being 2nd Tues | WMB to send dates to JJ. JJ to notify Cllr Jackson |
| 8 | Dates for forthcoming meetings – please bring diaries | Extra meeting planned for 3.8.15 to update our position following outcome of Grove Farm application | JJ to notify members |
| 9 | AOB | There was no other business and the meeting closed at 8.55 |  |

Signed:                                                                                      Date: