Misson Parish Council

Neighbourhood Plan 2 October 2023 update

Brief; update of the existing Neighbourhood Plan to take into account regional and national planning policies, information from the 2021 Census and clarification of minor details from the local community events held to date In July 2002 and January 2023

Funding; Nothing further to report in the period

Expenditure in the period; None. However, an invoice has been received from the planning consultant for the balance of their fee which is due upon conclusion of the Reg 14 period

Progress; The Executive Summary is printed and will be delivered with the Newsletter.

The Parish Clerk has digital copies of the summary and the draft Neighbourhood Plan for the Parish Council website

Posters are being designed and will be circulated around the Parish regarding the consultation and open event

Each member of the Steering Group has a hard copy of the plan should anyone wish to read it and details have been included in communications. Hard copies of the feedback form are also available

All the documents have also been uploaded to the BDC Planning website

Programme; Reg 14 consultation period commenced on 2 October 2023 as planned and will last at least six weeks until the middle of November 2023

An open event is planned for Saturday 21 October 2023 12-3pm in the Community Centre when members of the group and representatives from BDC will be in attendance to clarify any matters. A further event may be arranged towards the end of the period

Bassetlaw District Council will circulate to statutory consultees including neighbouring Parish Councils

Following the Reg 14 period, any changes will be discussed and included in the Plan prior the commencement of a Reg 15 period administered by BDC, presentation to the Independent Examiner and a possible referendum again administered by BDC. Timescales not known at this stage

Communication; Editorial has been included in Bawtry Today that was circulated to the Parish last week. In addition the Consultation period has been advised in the Misson Newsletter and social media.

The draft plan, design guide and feedback forms will be uploaded on MPC website w/c 2 October 2023

Feedback is possible either electronically or by hard copy

2 Oct 2023