Misson Parish Council

Neighbourhood Plan 2 July 2023 update

Expenditure in the period; None

There is an outstanding payment (£2813) to OpenPlan that is due upon completion of the Reg15/16 stage.

Funding; BDC has advised no progress in the identification of public sector funds for the completion of the Neighbourhood Plan, BDC has another 8 Plans in the same status.

Progress; None in the period; some details need updating prior to the Plan being approved by the Steering Group and moving to the Reg 14 stage

Current status of the existing Neighbourhood Plan; on hold pending confirmation of funding and further instruction from Misson Parish Council.

Programme; The overall programme is approximately 16 weeks behind programme due to the planning consultant taking longer to provide the final draft of the Plan and to incorporate BDC initial comments and lack of clarity of funding from Groundworks/Locality

The indicative programme below is the earliest period for completing the tasks

| Indicative timescale* | Community | Technical |
| --- | --- | --- |
| June |  | Reg 14 Consultation (6 weeks) |
| July |  |  |
| Aug |  |  |
| Sept | Local Community consultation event on the draft NP |  |
| Oct | NPSG to consider any changes proposed from Reg 14 Consultation | Statutory consultees invited to comment by Bassetlaw DC |
| Nov |  | Planning Consultant to update draft Plan |
| Dec/Jan |  | Regulation 15/16 submission (BDC) Once the consultation is underway, OpenPlan prepare draft versions of the additional documents required (Basic Conditions Statement Consultation Statement) for the submission to the Independent Examiner Review Statement (produced jointly with BDC, specifying the changes made over the original Neighbourhood Plan, and the anticipated scale of the review) |
| Feb 2024 |  | If no major changes made to policies BDC to submit to Ind Examiner. |
| March |  | Independent Examiner review |
| April |  | Possible referendum (subject to local elections |

Communication; No updates in the period

2 July 2023