Seend Parish Neighbourhood Plan Steering Group.

Notes of  meeting 26.07.2018  7.30pm The Pavilion

(Produced by GA 30.07.18)

Attended by : Georgina A’Bear Chair (GA), Kevin Rigg (KR),  Peter Newsom  (PN),Carole Vince (CV)

Apologies: Darren Nichols(DN), Aldetha Raymond(AR), Pamela Akerman(PA) &  Carola Thorpe(CT)

1 One member of the public.

2 Declaration of interest: None

Members Matter:- Sarah Chard resigned on 12th July’18. I would like to thank Sarah for all the work she has done for the group.

3 As there was no meeting held last month there are no minutes to approve

4. Matters arising:N/A

5.Local Green Space consultation.

We are nearly finished with the letter. There is additional wording to be added ref:- CT & CV e.mails.

Form Return Information:- By post or by hand to:- CV, PN & KR. They supplied their addresses to go on the letter. Also return by e.mail to group e.mail.

The return date has been agreed on 12th October so this allows for a couple of weeks after the October Spotlight has been circulated so that we can remind people to return form.

The letter, map & return form will be available on the website.

GA to check with GP(PS) re format of return so that it can be downloaded and completed  electronically.

Note:- This has been checked and GA also asked the form having no  name or date box on the form. The form is to be returned anonymously and this also means we do not have any issues with Data protection.

We agreed on 500 copies of 5 sides to be printed i.e.2500 sides of printing. The map is to be printed in colour.

Also required A5 envelopes.

Note:- GA has purchased 3 reams of paper, 200 envelopes (more to buy next week) and self adhesive labels to go on envelopes.

A quote  for printing to be obtained  from Mark Wood and also CV to ask about the community printer.

GA to e.mail a call out for volunteers with the prep. of the letters and the distribution.

Community Facilities. CV is happy with this and PS are continuing to work on it.

Vision. Those present were happy with the draft vision.

DRAFT NDP. Those present were happy for CT to take on the responsibility of the editorial work on this document.

6.CV has done a great job with the display material on the stand.

Seend Breakfasts. CV attended Saturday 14th July, PN attended Saturday 22nd July. GA to attend Saturday 28th July. PN brought the display stand & wristbands to meeting so GA has for Saturday.

Volunteers required for Saturday 25th August & Saturday 1st September.

Seend Flower Show. GA to set up the stand in the morning. Please let me know if you can volunteer to help on the stand during the afternoon.

7. GA to contact Amy on the website updates. Minutes Apr. & May’18. Change date for next meeting. We also need to add the Vision and when complete the L.G.S. information.

8. Jon Goman had kindly sent his apologies and sent a CPRE leaflet on the need for affordable homes.

9.No Spotlight article required this month as a double issue has gone out for Aug./Sep.’18

10. GA has circulated to the group the schedule of payments produced by the Parish Clerk.

This month the P.C. will be paying for Camelot Media £475.00 and Place Studio £2,170.80 (Inc.VAT)

11. Action Plan Review. Still no update oin this. Do we need it?PS to be asked about archiving the old information.

The meeting concluded at 8.50 pm.

Next public committee meeting August 30th 7.30pm  Irene Usher Memorial Hall.