Misson Parish Council

Neighbourhood Plan 2 September 2023 update

Brief; update of the existing Neighbourhood Plan to take into account regional and national planning policies, information from the 2021 Census and clarification of minor details from the local community events held to date In July 2002 and January 2023

Funding; David Hobson made a successful application on behalf of Misson Parish Council to complete the work to update the Plan. Essentially it is the amount not spent previously of the initial grant plus another provisional one day’s work for the planning consultant. The total amount is as summarised below;

| Item | Amount |
| --- | --- |
| Supporting community consultation | £1,013 |
| Preparing final documents | £1,800 |
| Additional advice from planning consultant | £900 |
| Allowance for further detail updates post Reg 14 period | £450 |
| 5 meetings in Community Centre | £100 |
| 3 editions of Misson Newsletter | £75 |
| Leaflet drop to all homes, organisations and businesses | £120 |
| Further 2 open days during Reg 14 period - community centre hire | £200 |
| Allowance for printed plans for Reg 14 consultation for people with limited Internet access | £500 |
|  | £0 |
| Total | £5,158 |

Expenditure in the period; None.

Progress; The draft Plan is being approved by the Steering Group. Once approval from steering group members is received the Reg 14 Consultation can commence

Programme; It is proposed that the Reg 14 consultation (6 weeks) will commence early October following receipt of the Executive Summary from the planning consultant

The Steering group will publicise in Bawtry Today, Posters around the Parish and social media.

The Plan will be uploaded onto the Parish Council website. The Planning Consultant is drafting an Exec Summary that will be distributed to the local community, organisations and businesses. An open event will be held mid-October and comments can be made either electronically or by letter

Bassetlaw District Council will circulate to statutory consultees including neighbouring Parish Councils

Communication; No updates in the period

2 Sept 2023