Warbleton Parish Council – Internal Audit Report – Summary of issues raised and proposed actions – Update September 2020

| Issue raised | Proposed action | Proposed timescale |
| --- | --- | --- |
| A . Appropriate Accounting Record |  |  |
| 1. (A1) Cash book to be updated after each payment made/monies received and reconciled to bank account | Chairman of F&GP Committee to review cashbook on monthly basis and report any issues to Full Council | 18th Monthly – ongoing- currently no issues |
| B. Financial regulations , documentation and approvals |  |  |
| 2. (B1) Update Standing Orders and Financial Regulations | Based on NALC model agreement | Completed |
| 3. (B2) Minutes of Annual Statutory Meeting to be completed | Minutes produced | Completed |
| 4. (B2/B6) Annual accounts and Annual Return (AGAR) to be approved by Council | Council to debate and agree at July meeting. Minutes to record approval to annual accounts and AGAR 3 form | Completed |
| 5. (B4) Improve reporting of reserves and CIL balances | Parish Clerk to incorporate into monthly budget monitor and to provide any explanation for changes to reserves | Ongoing – Monthly. Delays of bank statements in May, June, July has delayed process but now on track |
| 6. (B6) Publish Notice of Public Rights | Timetable to be approved at July Council meeting. Proposed Notice of Public Rights to be published on 1st September | Completed |
| C. Risk |  |  |
| 7. (C1) Loss of cash book and accounting data | Review as part of risk register, agree mitigating actions and present to Council for approval | Council in September. On September Agenda for approval |
| 8. (C2) Update and review risk register | Determination of a new risk register is currently underway. Will be reviewed by F&GP and presented to full Council | Council in September and reviewed annually thereafter. On September Council agenda. Due to time constraints unable to hold a F&GP meeting in advance |
| 9. (C2.1) Risk – Annual return | All councillors to receive a copy of Annual Return | 31st July – provided at July Council meeting |
| 10. (C4) No Asset Register | Parish Clerk has begun to compile an Asset Register based on historic records and councillor knowledge | Council in September and reviewed annually thereafter – review commenced and update a September Council |
| D. Budgeting and Precept |  |  |
| 11. (D1/D2) Income and reserves | Ensure budget process reviews income/reserves and records any outcome | January 2021 |
| 12. (D2.1) Treatment of VAT | Ensure VAT not included in budgeted income/spend but is considered for reconciling cash flows | January 2021 |
| 13. (D3) Use of current year forecast | Project current year expenditure as part of budget process and demonstrate within minutes | January 2021 |
| E. Receipts |  |  |
| 14. (E) Report any HMRC/PAYE refund as a credit to costs | None required | N/a |
| G. Employee Costs |  |  |
| 15. Demonstrate that payroll and employee records are in good order | Sample checks by F&GP Chairman | Quarterly – Completed - no issues |
| H. Assets |  |  |
| 16. (H1/2/3/4) Asset register | See item 10. Ensure Insurance Policy covers any assets on Register | September 2020 - September Council to review |
| I. Bank reconciliations |  |  |
| 17. (I1/2) Ensure monthly and annual bank reconciliation undertaken and reported to Council | Parish Clerk to complete and present to each full Council meeting | Monthly - reconciliations completed up to 30/6/20. Awaiting July/August Bank statements |
| 18. (I3) Bank Mandate | Review annually | December 2020 |